## Sheet1
DATE | TEST CASE/ SCENERIO | BUGS/ISSUES | DESCRIPTIONS | RISK LEVEL | TASK OWNER | TESTED BY | TESTED DATE | EXPECTED RESULTS | STATUS | UAT | QA COMMENTS | UAT COMMENT
2023-07-06 | Account Creation | Blank page on the sign-up page | When user navigate to create account page, there is a blank page showing by the right side. | Medium |  | Bukunmi, Samson, Paul | 2023-07-06 | Image or text rather than a blank page | Open
2023-07-06 | Onboarding Modal | Onboarding displaying as a page instead of modal | Onboarding modal not as in user specification | Medium |  | Bukunmi, Samson, Paul | 2023-07-06 | Onboarding modal should be as per user specification | Open
2023-07-06